## 19Apr24
Portfolio Status Report
Portfolio Delivery Roadmap
2024-04-04 | 2024-05-01 |  | 2024-06-01 |  | 2024-07-01 | 2024-08-01 |  | 2024-09-01 |  | 2024-10-01 | 2024-11-01 | 2024-12-01
SKU Existing
Akabot
Liquor license
CR 10.3 ( WF Trade contract)
Facility DC02
Upgrade: Sharepoint
Upgrade: UI\UX
Upgrade: DataSet
Uprade: Edoc
Portfolio Status |  |  |  |  | Portfolio Financials
Project |  |  |  |  | Project | Planned | Actual | Forecast | Variance | Note
SKU Existing | Schedule | Budget | Resources | Risks
Akabot | Schedule | Budget | Resources | Risks
Liquor licence | Schedule | Budget | Resources | Risks
CR 10.3 ( WF Trade contract) | Schedule | Budget | Resources | Risks
Facility DC02 | Schedule | Budget | Resources | Risks
Upgrade: Sharepoint | Schedule | Budget | Resources | Risks
Upgrade: UI\UX | Schedule | Budget | Resources | Risks
Upgrade: DataSet | Schedule | Budget | Resources | Risks
Uprade: Edoc | Schedule | Budget | Resources | Risks
Portfolio Status |  |  |  |  | Portfolio Budget
Project Status
SKU Existing
Phase | Start | End | Progress | Status | Risks, Issues, Dependencies or Concerns
Build | 2024-01-15 | 2024-05-10 | 95% | On track | có phát sinh CR dẫn tới kéo dài dự án | [7 empty] | On track
Test | 2024-05-12 | 2024-06-10 | 90% | On track | có thể triển khai UAT sớm hơn dự kiến 1 tuần (dự kiến UAT ngày 13/5/2024) | [7 empty] | On track
Deploy | 2024-06-12 | 2024-06-12 | 0% | Pending | [8 empty] | On track
Support | 2024-06-12 | 2025-06-12 | 0% | Pending
Akabot
Phase | Start | End | Progress | Status | Risks, Issues, Dependencies or Concerns
Build | 2024-03-18 | 2024-05-01 | 85% | On track | Làm trước 3CR của CR11.1 trong đợt này | [7 empty] | On track
Test | 2024-05-02 | 2024-05-13 | 65% | On track | Đang chờ FPT UAT con BOT - Cấp VPN và Tài khoản Edoc | [7 empty] | On track
Deploy | 2024-05-15 | 2024-05-15 | 0% | Pending | [8 empty] | On track
Support | 2024-05-15 | 2026-05-15 | 0% | Pending
Liquor licence
Phase | Start | End | Progress | Status | Risks, Issues, Dependencies or Concerns
Build | 2024-03-25 | 2024-05-29 | 41% | On track | mục tiêu tuần tiếp theo sử dụng tool AI nào cho phần nhận diện file ORC | [7 empty] | On track
Test | 2024-05-30 | 2024-06-29 | 0% | On track
Deploy | 2024-06-29 | 2024-06-29 | 0% | Pending
Support | 2024-06-29 | 2025-06-22 | 0% | Pending
CR 10.3
Phase | Start | End | Progress | Status | Risks, Issues, Dependencies or Concerns
Build | 2024-04-15 | 2024-05-31 | 14% | On track | [8 empty] | On track
Test | 2024-06-02 | 2024-06-14 | 0% | Pending
Deploy | 2024-06-16 | 2024-06-16 | 0% | Pending
Support | 2024-06-16 | 2025-06-16 | 0% | Pending
Facility DC02
Phase | Start | End | Progress | Status | Risks, Issues, Dependencies or Concerns
Build | 2024-04-17 | 2024-08-14 | 2% | On track | Đang cần chốt về vấn đề Orgchart với SAP, Thứ 5 25/4 user sẽ confirm SRS phần setting Danh mục | [7 empty] | On track
Test | 2024-08-15 | 2024-09-06 | 0% | Pending
Deploy | 2024-09-07 | 2024-09-08 | 0% | Pending
Support | 2024-09-07 | 2025-09-07 | 0% | Pending
Upgrade: Sharepoint
Phase | Start | End | Progress | Status | Risks, Issues, Dependencies or Concerns
Build | 2024-04-22 | 2024-06-10 | 5% | On track | cài 2 lần để tận dụng hạ tầng cũ | [7 empty] | On track
Test | 2024-06-12 | 2024-06-26 | 0% | Pending
Deploy | 2024-06-26 | 2024-06-26 | 0% | Pending
Support | 2024-06-26 | 2025-06-26 | 0% | Pending
Upgrade: UI\UX
Phase | Start | End | Progress | Status | Risks, Issues, Dependencies or Concerns
Build | 2024-06-15 | 2024-07-30 | 5% | On track | [8 empty] | On track
Test | 2024-07-30 | 2024-08-15 | 0% | Pending
Deploy | 2024-08-16 | 2024-08-16 | 0% | Pending
Support | 2024-08-15 | 2025-08-15 | 0% | Pending
Upgrade: DataSet
Phase | Start | End | Progress | Status | Risks, Issues, Dependencies or Concerns
Build | 2024-07-01 | 2024-10-30 | 0% | Pending | [8 empty] | On track
Test | 2024-10-30 | 2024-11-15 | 0% | Pending
Deploy | 2024-11-15 | 2024-11-15 | 0% | Pending
Support | 2024-11-15 | 11/15/205 | 0% | Pending
Uprade: Edoc
Phase | Start | End | Progress | Status | Risks, Issues, Dependencies or Concerns
Build | 2024-07-01 | 2024-12-15 | 0% | Pending | [8 empty] | On track
Test | 2024-12-15 | 2024-12-31 | 0% | Pending
Deploy | 2024-12-31 | 2024-12-31 | 0% | Pending
Support | 2024-12-31 | 2025-12-31 | 0% | Pending

## Lists
On track
Concern
Delayed
Pending